## Basic Project with Gantt _ Depe
At Risk | Task Name | Start Date | End Date | Assigned To | Duration | % Complete | Predecessors | Notes
| Phase 1 : Start | 2017-10-09 | 2017-10-20 |  | 10d | 11%
| Screen prototypes | 2017-10-09 | 2017-10-13 | iHealth | 5d
| Proposed architecture and the tools/languages | 2017-10-16 | 2017-10-20 | iHealth | 5d | 25%
| Presentation | 2017-10-20 | 2017-10-20 | iHealth | 1d
| Phase 2 : Develop | 2017-10-23 | 2017-11-10 |  | 15d
| partially functioning application | 2017-10-23 | 2017-11-03 | iHealth | 10d
| Polish | 2017-11-04 | 2017-11-10 | iHealth | 6d
| Presentation | 2017-11-10 | 2017-11-10 | iHealth | 1d
| Phase 3 : Final | 2017-11-13 | 2017-12-01 |  | 15d
| Final touch | 2017-11-13 | 2017-12-01 | iHealth | 15d
| Presentation | 2017-12-01 | 2017-12-01 | iHealth | 1d

## Comments
Row 3 | Sub-task 2 You can add discussions, notes, or emails to discussions. | Jenny Gruening | 13-06-27 上午9:02